Total Elder Care Collaborative (TEC-C)

Response to Request for Proposals: HSCRC Transformation Implementation Program

Submitted to:

hscrc.rfp-implement@maryland.gov

December 18, 2015

Lead Hospitals:

MedStar Good Samaritan Hospital

MedStar Union Memorial Hospital

Partners and Collaborators:

Greater Baltimore Medical Center

Action in Maturity (AIM)

Brinton Woods

Gilchrist Hospice Care

Keswick Multi-Care Center

Stadium Place

Prepared by: Members of the Total Elder Care Collaborative

Points of Contact:

Debi Kuchka-Craig, FHFMA

Corporate Vice President, Managed Care

Debi.Kuchka-craig@medstar.net

Kathy Talbot

Vice President of Rates and Reimbursement, MedStar Health

Kathy.A.Talbot@medstar.net

Table of Contents

Proposal Narrative	1

1.	Target Population	1

1. A.  Geographic Scope:	1

Table 1: List of ZIP Codes, Counties, and Cities	1

1. B.  Health Needs and Conditions to be Addressed:	2

Health Needs of Frail Elders	2

Figure 1: Map of Geographic Area Covered	2

Health Needs of Baltimore City	3

Table 2: Top Five Chronic Conditions in Baltimore City	3

Table 3: Frequency of Top 5 Chronic Conditions among all High-Utilizers in Baltimore City	3

Health Needs Alignment with Community Health Needs Assessments	3

2.	Proposed Program or Intervention(s)	4

2. A.  Proposed delivery/financing model:	4

Services and/or Interventions the Patients Would Receive	4

Target Population	4

Role of Each Participating Partner	5

Figure 2: Partners in Home-Based Primary Care	6

Table 4: Role of Each Community Partner	6

Infrastructure and Workforce Needs	7

Financing Model	7

2. B.  Discussion of the Proposed Program/Intervention:	7

Evidence Base for the Intervention	7

Innovative use of Health Information Technology	8

Patient-Centered Nature of the Intervention	8

Intervention Efforts Underway	8

How Additional Support Bolsters Immediate Implementation	8

Complementary Nature of the Intervention	9

Table 5: Complementary Infrastructure Investments	9

Distinct Nature of the Intervention	11

Improving Population Health with TEC-C Teams	11

Fit with Overall Hospital Strategic Transformation Plan	11

Table 6: TEC-C Alignment with Hospital Strategic Transformation Plans	11

3.	Measurement and Outcome	12

3. A.  Measuring Outcomes	12

Expected Outcomes, Baseline Data and Measures	12

Table 7: Core Outcome Measures	12

How the Target Population Positively Impacts Key Outcome Measures	13

3. B.  Measuring Process	13

Baseline Data, Process, and Programmatic Measures	13

Table 8: Core Process Measures	14

Table 9: Program Specific Measures	14

4.	Return on Investment	15

Table 10: Core Return on Investment Measures	15

4. A. Alignment with Maryland All-Payer Model Goals and Requirements 	16

4. B. Expected Hospital ROI 2017-2019 	16

4. C. Utilizing, Apportioning, and Applying the ROI:	16

4. D. Reduction in Total Cost of Care beyond the Hospital: 	16

5.	Scalability and Sustainability	16

5. A. Sustainability of the Intervention:	16

5. B. Expansion of the Intervention:	17

5. C. Partner Demonstrated Commitment:	17

6.	Participating Partners and Decision-Making Process	17

6. A. Participating Partners and Shared Decision Making Process	17

6. B. Formalized Governance Structure	18

6. C. Roles, Responsibilities, and Funding for each Partner 	18

Table 11: Partner Roles and Funding	18

Other Proposal Requirements	19

7.	Implementation Work Plan 	19

Please see the separate pdf file as part of this proposal submission.	19

8.	Budget and Expenditures	20

8. A. Line Item Budget on Template	20

9.	Budget and Expenditures Narrative 	21

9. A. MTEC Intervention	21

Workforce/Type of Staff match	21

IT/Technologies	21

Other implementation Activities	21

Other Indirect costs	22

Other Reimbursements	22

Total Expenses/investments	22

9. B. Total Cost of the Intervention:  	22

9. C. Percentage Total Investment Covered by Award:	22

9. D. Dispersion of Funds to Partners	22

10.	Summary of Proposal	23

11.	Appendices	26

Appendix A: Map of Coverage Areas for TEC-C and GBMC Support Our Elders	27

Appendix B.  Chronic Condition Prevalence by County	28

Appendix C.  TEC-C Governance Structure	30

Appendix D.  Signed Letters of Commitment	31

12.	References	42

# Proposal Narrative

# Target Population

## 1. A.  Geographic Scope:

Nationwide, there is an increasing population of elders with severe chronic illness who struggle to find healthcare that addresses their entire scope of medical and social needs (Fitzpatrick, Powe, Cooper, Ives, & Robbins, 2004).  Such frail elders often receive care from a fragmented array of institutions and specialists that focus on specific parts of the body but not the overall person.  Frail elders face obstacles to good primary care due to physical disability, transportation problems, poor cognitive function, or inadequate social supports.  Many experience unnecessary hospitalizations due to inadequate urgent and primary care.  These ill elders need the most intensive monitoring, but have the hardest time getting to a doctor's office.  The net results are unfavorable clinical outcomes, a difficult experience for patients and families, and excessively high healthcare costs (Fried, Ferrucci, Darer, Williamson, & Anderson, 2004).  Maryland, specifically the county of Baltimore City, has a high density of high-cost Medicare beneficiaries.  An internal data analysis conducted by the National Minority Quality Forum in 2015 as part of a contractual relationship with MedStar found that subgroups of this population have average annual Medicare costs that range from $12,000 to $140,000/year.   The Total Elder Care Collaborative (TEC-C) seeks to demonstrate the efficacy and scalability of the shovel-ready MedStar Total Elder Care (MTEC) home-based primary care model for complex older patients in order to: 1) improve clinical outcomes; 2) improve the patient and family experience; and 3) lower the total costs of care.  The TEC-C will achieve this vision by delivering home-based primary care to elders in eight ZIP codes in the county of Baltimore City, including the cities of Baltimore, Roland Park, Govans, Idlewylde, Loch Hill, and Northwood (Table 1).

### Table 1: List of ZIP Codes, Counties, and Cities

| ZIP code | County | Incorporated Cities |
| --- | --- | --- |
| 21206 | Baltimore City | Baltimore |
| 21210 | Baltimore City | Baltimore; Roland Park |
| 21211 | Baltimore City | Baltimore |
| 21212 | Baltimore City | Baltimore; Govans |
| 21214 | Baltimore City | Baltimore |
| 21213 | Baltimore City | Baltimore |
| 21218 | Baltimore City | Baltimore |
| 21239 | Baltimore City | Baltimore; Idlewylde; Loch Hill; Northwood |

The geographic nexus of TEC-C is a network of two lead hospitals – MedStar Good Samaritan Hospital (MGSH) and MedStar Union Memorial Hospital (MUMH), along with 6 committed partners including: Greater Baltimore Medical Center Support Our Elders (GBMC SOE), Action in Maturity (AIM), Brinton Woods, Gilchrist Hospice Care, Keswick Multi-Care Center, and Stadium Place, which all provide healthcare and community-level services to this area.  Figure 1 illustrates the service area by ZIP codes that surround each hospital.  The ZIP codes selected for TEC-C represent one or more of the Community Benefit Service Areas (CBSA) for each lead hospital, and have high numbers of Medicare discharges, and readmissions (within 90 days of discharge).  For a map of the total coverage area for the two lead hospitals for TEC-C and the coverage area for GBMC Support Our Elders program, please see Appendix A.

### Figure 1: Map of Geographic Area Covered

## 1. B.  Health Needs and Conditions to be Addressed:

### Health Needs of Frail Elders

Unlike traditional disease management programs, the MedStar Total Elder Care (MTEC) model of home-based primary care focuses on the overall needs of high-risk elders, regardless of specific disease conditions.  The major health needs for this population are functional disability, care coordination, social support services, management of multiple severe chronic illnesses, and palliative and end-of-life care.

The targeted geographic area in Baltimore includes a population of elders that have multiple chronic conditions. The major conditions found in this population include dementia, stroke, psychiatric disease, congestive heart failure, chronic obstructive pulmonary disease (COPD)/respiratory failure, severe chronic kidney disease, cancer,   diabetes, hypertension, and falls.  Typically, several of these conditions are present in one individual. These frail elders have high symptom burden and functional impairment, which predict greater mortality and higher medical costs, including a risk of emergency department visits, hospital admission, and use of postacute care services (De Jonge et al., 2014).

TEC-C will aim to improve outcomes for frail elders meeting the following criteria: 1) reside in one of the eight targeted ZIP codes, 2) ages 65 or older, 3) have two or more serious chronic illnesses, 4) functional impairment (in activities of daily living (ADLs) or instrumental activities of daily living (IADLs)) that limit their ability to get to doctor’s office, and 5) are willing to transfer primary care to the TEC-C team.  In addition to these five criteria, elders who have a history of hospitalization in past year and a history of a post-acute Medicare episode (home health or inpatient rehab) represent an even higher cost subgroup.

We anticipate that the MTEC model will reduce overall utilization by better management of patients with multiple severe chronic illnesses.  Given the advanced illness in this population, MTEC teams also help patients and families with palliative and end of life care, and caregiver support and social services..

### Health Needs of Baltimore City

According to HSCRC Abstract Data (DHMH & HSCRC, 2015), among Medicare beneficiaries in the county of Baltimore City, the top five chronic conditions were:  1) hypertension, 2) hyperlipidemia (also known as “high cholesterol”), 3) diabetes, 4) arthritis, and 5) ischemic heart disease (also known as “coronary artery disease”.  These top five health needs are supported by data from existing Community Health Needs Assessments (CHNAs).  Table 2 summarizes the top five chronic conditions affecting Medicare FFS beneficiaries living in Baltimore City according to HSCRC Abstract Data (See Appendix B for graphic depictions of the prevalence of chronic conditions among Medicare fee for service (FFS) patients in Baltimore City).  Table 3 summarizes the frequency of these top five chronic conditions among all high-utilizers (N=9,947) in Baltimore City.

### Table 2: Top Five Chronic Conditions in Baltimore City

| Condition | Average condition prevalence among Medicare FFS beneficiaries |
| --- | --- |
| Hypertension | 60.01% |
| Hyperlipidemia | 48.79% |
| Diabetes | 30.09% |
| Arthritis | 28.78% |
| Ischemic Heart Disease | 29.19% |

### Table 3: Frequency of Top 5 Chronic Conditions among all High-Utilizers in Baltimore City

| Condition | # County High -Utilizers | % of County High-Utilizers |
| --- | --- | --- |
| Hypertension | 7,827 | 78.69% |
| Hyperlipidemia | 4,773 | 47.98% |
| Diabetes | 4,533 | 45.57% |
| Arthritis | 2,140 | 21.51% |
| Ischemic Heart Disease | 3,583 | 36.02% |

### Health Needs Alignment with Community Health Needs Assessments

The MedStar Good Samaritan Hospital Community Health Needs Assessment (CHNA) identified heart disease, hypertension, and diabetes as three of its areas of focus for disease prevention and management of the Govans community, the community benefit service area (ZIP code 21212).  The MedStar Union Memorial CHNA also identified heart disease and access to care as areas of focus on communities within the North Central Baltimore City area.  All three of the community benefit service areas ZIP codes identified in this CHNA are ZIP codes targeted for TEC-C efforts (ZIP codes 21211, 21213 and 21218) (MedStar Health, 2015).

Heart Disease, Hypertension, and Hyperlipidemia:  Heart disease is the leading cause of death in Baltimore City and contributes to high utilization (Centers for Disease Control and Prevention, 2015). Lipid disorders, cardiac arrhythmia, and coronary artery disease are all chronic conditions related to the heart (Assmann & Schulte, 1992; National Guideline Clearinghouse, 2012).  These conditions increase the risk of stroke as well (Centers for Disease Control and Prevention, 2014).  The age-adjusted death rate due to stroke in Baltimore City is decreasing (from 51/100,000 people in 2009 to 48/100,000 people in 2012) but remains significantly higher than the state (38/100,000 people) and national averages (38/100,000 people). In Baltimore City, the prevalence of hypertension (35 percent) and hyperlipidemia (30 percent) contributes to the age-adjusted death rate due to heart disease and stroke.  The rate of emergency department visits for hypertension in Baltimore City is 600/100,000 people, compared to 246/100,000 in Maryland (MedStar Health, 2015). The prevalence of hypertension and hyperlipidemia in Baltimore City exceeds Healthy People 2020 goals (35 percent vs. 27 percent, and 33 percent vs. 14 percent, respectively).  Heart disease, hypertension, and hyperlipidemia are among the chronic conditions typically found in the targeted frail elderly population (Department of Health and Human Services, 2010).

Diabetes:  Diabetes is a chronic condition that leads to high rates of healthcare utilization and mortality.  As reported by the CHNAs for both hospitals, the rate of emergency department visits due to diabetes in Baltimore City has increased from 444 visits/100,000 people in 2010 to 502 visits/100,000 people in 2013 (MedStar Health, 2015). The age-adjusted death rate due to diabetes is 30 deaths/100,000 people in Baltimore City, compared to 21/100,000 nationally (Maryland Department of Health and Mental Hygiene, 2013).  The rate of emergency department visits due to diabetes has increased from 444 visits/100,000 people in 2010 to 502 visits/100,000 people in 2013 (MedStar Health, 2015). Diabetes is among the chronic conditions typically found in the targeted frail elderly population.

Access to care:  The MedStar Union Memorial CHNA identifies access to care as an issue for the community benefit service area identified.  When considering availability, the patient-provider ratio is relatively low for primary care physicians (937:1) and mental health providers (392:1), placing Baltimore City in the 90th percentile in the country. The Baltimore City Health Department set a Healthy Baltimore 2015 goal to reduce the percentage of insured residents who report having unmet medical needs in the last 12 months to 12.2 percent overall (MedStar Health, 2015; Robert Wood Johnson Foundation, 2015; Baltimore City Health Department, 2014).  Access to care is also an issue for the elders with severe chronic illness.  These frail elders face barriers to access to care such as disability, transportation problems, poor cognitive function, or inadequate social supports (Fitzpatrick et al., 2004).  The TEC-C service model will improve access to comprehensive and coordinated care for this population, which will improve clinical outcomes and the patient and family experience, and decrease the total costs of care.

# Proposed Program or Intervention(s)

## 2. A.  Proposed delivery/financing model:

### Services and/or Interventions the Patients Would Receive

Frail elders will receive services from MedStar’s shovel-ready, nationally recognized house call model of primary care (De Jonge et al., 2014).  This home-based primary care program was previously known as the Medical House Call Program (MHCP) when developed in Washington D.C. and is now known as MedStar Total Elder Care (MTEC).  Since 1999, MedStar Health has operated an MTEC-style program through MedStar Washington Hospital that cares for ill elders at home and across all settings.  MTEC teams are guided by four principles: 1) a humane approach to care of frail elders; 2) state-of-the-art diagnostic tests, treatment, and technology at home; 3) coordination of all medical and social services across settings, until the end of life; and 4) economic viability for patients, providers, and payers.

MTEC consists of modular and geographically-targeted teams who serve the most ill subgroup of elders in a catchment area, usually within a 20-minute driving radius.  Each team module consists of 10 staff, including geriatricians, nurse practitioners, care coordinators, triage nurses, and social workers.  The core element of success is ability to offer a single, comprehensive source of home-based medical and social services for patients and their families.  Core services include home-based primary care, 24/7 on-call medical staff, continuity to the hospital, intensive social services, and coordination of all specialty and ancillary services.   As of 2015, MTEC has served over 3,200 elders in Washington D.C. and has an active census of 620 patients.  Each team can serve a total of 300-350 frail elders.   The goal of the TEC-C is to demonstrate the scalability of this model to Maryland, beginning with eight targeted ZIP codes in the county of Baltimore City.

### Target Population

The target population for the TEC-C care model is elders with severe and disabling chronic illness.  These ill elders have difficulty getting to a doctor’s office and have high annual Medicare costs, usually over $25,000 per year, and even higher in Maryland.  According to an internal analysis conducted by JEN Associates, Inc in 2012, such patients represent about 5% of Medicare beneficiaries, many of whom are also eligible for the Medicare demonstration project, Independence at Home (IAH).   This analysis found that IAH-eligible patients had a significantly high rate of 30 day readmissions among all Medicare FFS beneficiaries, including 29% of all Medicare FFS hospitalizations even though IAH-eligibles were just 4% of the Medicare FFS beneficiary population.  This population, while small in number, represents a substantial proportion of Medicare expenditures (Congress of the United States Congressional Budget Office, 2005).  For the purposes of TEC-C, the target patients are defined as any individual who:

- Resides in one of the eight targeted ZIP codes;

- Is age 65 or older;

- Has two or more serious chronic illnesses;

- Has functional impairment (in activities of daily living (ADLs) or instrumental activities of daily living (IADLs)) that limit their ability to get to doctor’s office; and

- Is willing to transfer primary care to the TEC-C team.

In addition to these five criteria, we will target elders who also have a history of hospitalization in the past year and a history of a post-acute Medicare episode (home health or inpatient rehab), who represent an even higher cost subgroup.

We will identify TEC-eligible patients from referrals from community partners, hospital discharge teams, and office-based medicine practices in the catchment area.  We can also screen databases of hospital discharges and use a sophisticated risk-stratification tool developed by Evolent Health, called IdentifiTM to identify elders who are at high-risk due to high utilization rates, severe chronic illnesses, and functional disability.

### Role of Each Participating Partner

The main goal of this grant is to replicate a successful home-based primary care model that addresses the needs of frail elders with severe chronic illness, disability, and high costs.  MedStar Health is expanding the MTEC model into Baltimore to serve ZIP codes 21239, 21210, 21211, 21212, 21213, 21214, 21218, and 21206. We have already hired an experienced and expert lead physician and expect to start seeing patients in April, 2016.   Founded in 1999 in Washington D.C., the MTEC model has a history of meeting patient and family needs with dedicated home-based primary care and reducing Medicare costs by 17-20% (De Jonge et al., 2014; MedStar Washington Hospital Center, 2015).

#### Greater Baltimore Medical Center

The MTEC expansion through TEC-C will occur within the natural catchment zip codes of MedStar Good Samaritan Hospital and MedStar Union Memorial Hospital, which are adjacent to the southern catchment area of Greater Baltimore Medical Center (GBMC).  Given the robust services already in place at GBMC Geriatrics, we plan to partner with GBMC to meet the needs of patients in the region with collaboration on home-based primary care, hospital services, hospice, and sub-acute care.

The interdisciplinary home-based primary care teams of TEC-C and GBMC will jointly cover a larger geography than either can do on their own.  This offers an opportunity to work together and ensure that patients from both systems are managed appropriately across settings and discharged safely to their respective care teams in the community.

Specifically, TEC-C teams and GBMC Geriatrics will refer eligible patients living in ZIP codes beyond their own service area to the other’s programs.  We will engage in joint efforts to ensure a standardized approach to clinical care and safe hand-offs between settings, and share our knowledge of high-quality community service partners.  We will track common outcome metrics and share best practices from our respective clinical services.  This collaborative will ensure that ill and high-cost elders in Baltimore region receive coordinated and skilled geriatrics home-based care across all settings.

#### Community Partnerships

### Figure 2: Partners in Home-Based Primary Care

Community partnerships have been a key component to MTEC’s past success in meeting the medical and social needs of the frail elders.  Figure 2 illustrates the types of partners involved in MTEC’s home-based primary care program and the relationship with the MTEC care team.  These include: ER and hospital; aides, food, home environment, and legal counsel; home rehabilitation, nursing, and hospice; home delivery pharmacy/DME oxygen; transportation, labs, X-ray; and subspecialists, and sub-acute rehabilitation.

To effectively scale MTEC teams to Baltimore City through TEC-C, we have established local partnerships that will meet the medical and social needs in Figure 2.   Each Baltimore partner has documented this commitment through signed letters (see Appendix D).  Table 4 lists each community partner and the role of each.

### Table 4: Role of Each Community Partner

| Name of Partner | Role in TEC-C |
| --- | --- |
| Action in Maturity (AIM) | Provide transportation and social services to aging adults to support their ability to live independently within the community as long as possible. |
| Brinton Woods | Provides 24-hour licensed nursing care in a caring, home-like environment; provides short-term rehabilitation and long-term care services |
| Gilchrist Hospice Care | Provides high quality hospice services (home-based and inpatient) including medical and nursing care, social work support, home health and volunteer assistance, and spiritual and grief counseling |
| Keswick Multi-Care Center | Inpatient and Outpatient Rehabilitation programs provide customized care and support upon older adult discharge from the hospital |
| Stadium Place | Provides housing with supportive services including assessments, orientations, assistance with social service concerns, linkages to community services for residents, and medical services. |

#### MedStar Health

The lead hospitals for TEC-C are MedStar Good Samaritan Hospital (MGSH) and MedStar Union Memorial Hospital (MUMH).  MGSH will provide the base for hospital care when needed and both MGSH and MUMH will function as important hubs for identification and enrollment of new patients for TEC-C.  MedStar Total Elder Care will provide the administrative and clinical operations for the mobile TEC-C primary care team.  MGSH’s Center for Successful Aging will function as the community resource partner given its current relationships to all community partners included in TEC-C.  It will also function as a clinical partner to offer office-based care and skilled nursing facility care when needed. MedStar Visiting Nurses Association will provide a wide array of skilled home services such as nursing, infusion treatment, physical therapy, and occupational therapy.  MedStar Institute for Innovation will function as the innovation partner for effective use of technology and organizational change.

#### Other Partners

JEN Associates, Inc and the MedStar Health Research Institute’s Health Services Research experts and its Department of Biostatistics and Bioinformatics will collaborate to ensure high-quality statistical and cost-level evaluation of the services provided under this initiative. They will also collaborate and work closely with the TEC-C team to ensure the monitoring and reporting of core outcome, process, and programmatic measures identified in Tables 7-9.

### Infrastructure and Workforce Needs

TEC-C will build two MTEC teams over the three years of the grant.  This number of teams is based on past experience of program growth.  Each team will include 10 staff; including  geriatricians, nurse practitioners, care coordinators, triage nurses, case managers, and social workers who can serve approximately 300-350 frail elders in a targeted geography.   Each TEC-C team expects to enroll 300 patients per year, based on prior history and on capacity of the teams, with estimated 20% annual mortality rate (De Jonge et al., 2014).   The first care team will begin servicing frail elders in the targeted ZIP codes in April, 2016 and grow to full capacity in about 18 months.  After the first care team reaches full capacity a second care team will begin servicing frail elders in targeted ZIP codes.

TEC-C has established clinical and administrative leadership.  Dr. Eric DeJonge, co-founder of the MTEC model in 1999, will serve as the Executive Director for TEC-C.  Julie Beecher, will provide administrative oversight of TEC-C teams.  These leaders are hiring the following staff for each team: 2 geriatricians, 2 nurse practitioners (NP), 2 care coordinators, 1 office triage nurse (RN), and 2 social workers.  The TEC-C community partners provide existing additional interdisciplinary staff (e.g. ER and hospital; home health aides, home rehabilitation, nursing, and hospice; home delivery pharmacy/DME oxygen; transportation, labs, X-ray; and build or partner for the following supplemental services: delivery of medications and supplies, security escort services, and weekend nursing services).  Additional infrastructure and workforce needs are itemized in the budget and described in the budget narrative.

### Financing Model

In addition to the funding from this award, TEC-C plans a similar reimbursement model based on its experience with MTEC in DC. These reimbursements include fee-for service health insurance revenues and IAH Medicare shared savings to a subset of eligible patients. The IAH Medicare Demo was expanded for 2 additional years into calendar year 2017.  Additional details on financing of the program can be found in sections 4, 8 and 9 of this proposal – the Return on Investment and Budget sections.

## 2. B.  Discussion of the Proposed Program/Intervention:

### Evidence Base for the Intervention

The Medical House Call Program, now known as MTEC,  has received local and national recognition for innovation in elder care and serves as one of the clinical sites for the Independence at Home Act (Section 3024), a Medicare pilot program included in the 2010 Affordable Care Act (De Jonge et al., 2014; MedStar Washington Hospital Center, 2015).

The Medicare Independence at Home (IAH) Demonstration works with medical practices to test the effectiveness of home-based primary care services.  The goal is to demonstrate if providing home-based services improves care for Medicare beneficiaries with multiple chronic conditions, improves patient and caregiver satisfaction, and leads to lower total costs.  IAH model of home-based primary care focuses on patients with multiple chronic conditions and functional limitations.  Such providers have  the opportunity to spend more time with patients, perform assessments at home, and assume accountability for all aspects of the patient’s care (Centers for Medicare & Medicaid Services, 2015).

MedStar Health’s participation in IAH since 2012 has found that that home-based approach ensures better care and patient experience, and reduces total Medicare costs.  MTEC participated in IAH as part of a Mid-Atlantic Consortium which included house call programs at Virginia Commonwealth University and the University of Pennsylvania.  Year 1 IAH results for the Mid-Atlantic Consortium demonstrated over the period of September 1, 2012 – August 31, 2013 that participants in the program:

- have fewer hospital readmissions within 30 days,

- have follow-up contact from their provider within 48 hours of a hospital admission,

- have their medications identified by their provider within 48 hours of discharge from the hospital,

- have their preferences documented by their provider, and

- use inpatient hospital and emergency department services less for conditions such as diabetes, high blood pressure, asthma, pneumonia and urinary tract infection.

- Reduced per capita total National Medicare costs by 20%, or over $12,000 per patient/ year

The Mid-Atlantic Consortium met all six IAH quality measures, reduced per capita Medicare costs by 20 percent, and received a $1.8 million payment from CMS in July, 2015.  MedStar Washington Hospital Center, original home of MTEC, received a 60% share of this $1.8 million savings payment because their program served 60% of the patients in the Consortium (MedStar Washington Hospital Center, 2015).

In October, 2014, Journal of American Geriatrics Society published several studies that showed the home-based primary care model reduce total costs of care by 12-17% and achieved high levels of patient and family satisfactions (De Jonge et al., 2014; Boling & Leff, 2014; Edes et al., 2014).

These recent peer-reviewed studies and MTEC’s successful participation in IAH provides evidence of the clinical and financial efficacy of the model.  We hypothesize that Baltimore City elders enrolled in MTEC teams will experience similar quality indicators and significant Medicare savings as a result.

### Innovative use of Health Information Technology

The MedStar Institute for Innovation (MI2) has been a critical partner for MTEC, supporting MTEC’s use of mobile health information technology.    MTEC actively uses the CRISP Health Information Exchange to track their entire population across settings.  This includes a daily report of any patient admitted to an ER or hospital in the region.  MTEC also uses a mobile, wireless electronic health record (EHR), which is viewable across settings.  MTEC is currently piloting the use of GPS technology to track clinicians in the field and increase efficiency of scheduling by geographic location.  MI2 will function as a critical partner for the TEC-C to find innovative solutions for building a real-time data management system from multiple databases for frail elders in Baltimore City.

### Patient-Centered Nature of the Intervention

The MTEC model supports patient-centered care in a person’s home, featuring an interdisciplinary mobile, care team.  The care team tailors care plans to the needs of each frail elder with multiple chronic illnesses and functional limitations. The care team is responsible for the coordination of every aspect of a patient’s medical and social needs.  To effectively tailor care plans, the team engages the frail elder, families, other providers, and community resources.  The care team consistently solicits and documents patient preferences for advance directives and goals of care.

### Intervention Efforts Underway

Since 1999, MedStar Health has operated an MTEC program in the District of Columbia (DC) area, and will continue to serve this geographic location.  In addition, MTEC will continue to participate as one of the clinical models for IAH as it has since 2012.  MTEC will continue to provide: 1) a humane approach to care of frail elders; 2) state-of-the-art diagnostic tests, treatment, and technology at home; 3) coordination of all medical and social services across settings, until the end of life; and 4) economic viability for patients, providers, and payers.  Given the past success of MTEC in DC, we have elected to expand the MTEC model to Maryland and across the MedStar Health region.

As part of this existing expansion, we have hired a new lead physician and established clinical collaborations with the MedStar Center for Successful Aging at Good Samaritan and with GBMC Geriatrics services.

### How Additional Support Bolsters Immediate Implementation

Additional support of TEC-C under this grant will accelerate efforts to expand a shovel-ready, cost-saving MTEC program.  HSCRC grant support will:

- Support funding of core clinical staff to increase capacity for serving more patients;

- Accelerate efforts to build essential infrastructure of information systems and data analytics to track population outcomes from multiple settings and digital databases;

- Foster collaborations with other key community partners;

- Accelerate efforts to build the evidence-base for the home-based primary care model and translate that success to other Maryland hospitals

- Allow us to identify high-cost eligible patients in our ZIP code areas, and to demonstrate positive ROI for the clinical intervention.

### Complementary Nature of the Intervention

TEC-C complements the programs underway based on our lead hospitals’ ongoing infrastructure investments.  Table 5 highlights infrastructure investments for each lead hospital, and explains the complementary nature of TEC-C to those investments.

### Table 5: Complementary Infrastructure Investments

| MedStar Good Samaritan Hospital (MGSH) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Intervention | Investment Category | Description |  | Complementary nature of TEC-C |
| Center for Successful Aging | Provider/care team | Opened the MGSH Center for Successful Aging to ensure patients are getting a holistic (vs episodic) approach to their health in the outpatient setting resulting in less admissions to the hospital |  | TEC-C is a home-based model of comprehensive primary care services. TEC-C partners with MGSH Center for Successful Aging to send and receive referrals from this office-based and skilled nursing facility Geriatrics programs. |
| Palliative Care | Provider/care team | Established a palliative care team to provide better end of life care to the community. |  | TEC-C addresses the medical and social needs of frail elders, which includes palliative services. TEC-C will collaborate as needed with the palliative care team at MGSH. |
| Psychiatric Services | Provider/care team | Expanded the MGSH outpatient Psychiatric clinic by 30% to ensure patients are getting appropriate treatment in the outpatient setting resulting in less admissions to the hospital |  | TEC-C addresses psychiatric needs for all frail elders. TEC-C efforts are aimed at reducing burden of mental health illness, and utilization, including psychiatric admissions. |
| Medication Reconciliation-Congestive Heart Failure (CHF) | Patient-centered | Medication management for CHF patients to ensure proper medication prescription and patient education; reduce readmissions related to failure to take prescribed medications |  | TEC-C efforts are aimed at reducing utilization such as readmission. |
| Bridge Clinic | Provider/care team | Bridge clinic established for patients that are being discharged that do not have adequate primary care coverage. This clinic provides valuable post acute follow up to ensure patients receive the care they need to prevent future admissions and better manage their care in the outpatient setting |  | Frail elders referred to the Bridge clinic who are eligible will be considered for enrollment in TEC-C |
| Post Acute Care Coordination (PACC) | Provider/care team | PACC resources to identify and screen patients with high risk conditions, and collaborate with the clinical and case management teams to smoothly transition patients to the next level of care supporting the hospital’s efforts to reduce readmission. |  | TEC-C is a care model for frail elders aimed at reducing utilization. Frail elders identified through PACC who are eligible for TEC-C will be considered for enrollment in TEC-C |
| MedStar Union Memorial Hospital (MUMH) |  |  |  |  |
| Intervention | Investment Category | Description | Complementary nature of TEC-C |  |
| Bridge Clinic | Patient centered | Providing ER/Hospital Admission patients follow-up appointments within 3-5 days after discharge or admission to decrease the overall readmission rate. | TEC-C provides proper follow-up appointments for all frail elders after discharge or admission aimed at reducing utilization. Frail elders referred to the Bridge clinic who are eligible for TEC-C will be considered for enrollment in TEC-C |  |
| CHF COPD Navigator | Provider/care team | One clinical Nurse FTE to provide education, support, and care coordination for patients who are in the acute care setting with a diagnosis of congestive heart failure. | Frail elders referred to the CHF/COPD Navigator who are eligible will be considered for enrollment in TEC-C |  |
| Case Managers and Social Workers Assistance | Provider/care team | Nurse Case Managers and Social Workers have taken on the responsibility for ensuring that patients have the ability to get their medications and that they have follow up with their primary care provider arranged before discharge. Barriers to care compliance are assessed (transportation, housing, etc.) | Frail elders referred to the Case Managers and Social Workers at MUMH who are eligible for TEC-C will be considered for enrollment in TEC-C |  |
| ED Navigator for Frequent Fliers | Provider/care team | Provide patient navigator coverage for the Emergency Department to improve transition from the hospital to community resources and minimize readmissions. | Frail elders eligible for TEC-C who are identified by the ED Navigator will be considered for enrollment in TEC-C. |  |
| Inpatient Navigators for follow-up appointments | Provider/care team | Provide patient navigator coverage for Inpatient Department to improve transition from the hospital to community resources and minimize readmissions. | Frail elders eligible for TEC-C who are identified by Inpatient Navigators will be considered for enrollment in TEC-C. |  |
| Palliative Care | Patient centered | Palliative medicine specialists consult service providing hospital-wide consultation for patients with advanced serious illness to improve care for patients with advanced illness and support them in avoiding unwanted and burdensome medical care. | TEC-C addresses the medical and social needs of frail elders, which may include the need for palliative services. TEC-C will collaborate as needed with the palliative care team at MUMH. |  |
| Post Acute Care Coordination (PAAC) | Patient centered | Discharge planning services | TEC-C is an effective care model for frail elders aimed at reducing utilization, including effective discharge planning. High risk frail elders identified through PACC who are eligible for TEC-C will be considered for enrollment in TEC-C |  |

### Distinct Nature of the Intervention

The MTEC model of home-based primary care is a distinctive elder care model because it has operated for 16 years in D.C., has published data in 2014 on good clinical outcomes and cost savings, and is the only area program to serve as a Medicare IAH demo site.   MTEC is replicating in Baltimore in order to reproduce these results in a new geography with a similar population.   MTEC teams offer a comprehensive array of medical and social services at home, oversee all hospital care, and incorporate social work services into the core operations. Other programs provide Medicare skilled Home Health; however, MTEC is one of the few local medical programs with extensive experience as a holistic home-based medical care program for frail elders.

### Improving Population Health with TEC-C Teams

The expansion of MTEC to Maryland through TEC-C can help improve the health of the Maryland population in the following ways:

- Provides home-based medical care to complex frail elders, thereby relieving office providers of managing complex cases.  This increases the capacity of office practices to serve a higher volume of less complex cases.

- Aligns with the Institute for Healthcare Improvement’s Triple Aim to  improve the patient experience of care, improve the health of populations, and reduce the per capita cost of health care (Institute for Healthcare Improvement, 2015).

- Optimizes the care coordination of frail elders in a home-based setting, thereby reducing caregiver and family burden, such as need to miss work and adding supportive services in the home

- MTEC teams use social workers to coordinate daily support services for frail elders and families, with the goal of enhanced personal safety and prevention of nursing home placement

- MTEC has demonstrated a 17-20% reduction of care costs.  We anticipate similar cost reductions in Maryland.  These cost reductions contribute to the overall sustainability of Medicare.

### Fit with Overall Hospital Strategic Transformation Plan

The MTEC program planned through TEC-C aligns with the overall strategic transformation plans for both lead hospitals – MedStar Good Samaritan Hospital (MGSH) and MedStar Union Memorial Hospital (MUMH).  Each Strategic Transformation Plan includes the expansion of MTEC to the MGSH and MUMH catchment areas.  In addition, Table 6 highlights additional ways TEC-C aligns with these transformation plans.  The hospital associated with each strategy is indicated in parentheses.

### Table 6: TEC-C Alignment with Hospital Strategic Transformation Plans

| Strategy | TEC-C Alignment |
| --- | --- |
| Expand the Center for Successful Aging which changes the care model from an episodic design for caring for elderly patients to a holistic approach to caring for these patients. (MGSH) | TEC-C partners with MGSH Center for Successful Aging to send and receive referrals from this office-based and skilled nursing facility Geriatrics programs. |
| Implement Plan-Identifi. Plan-Identifi uses data and information from multiple sources including electronic health records and CRISP, along with other sources when available (i.e. pharmacy, lab, and claims information). This data, coupled with a sophisticated analytics engine, risk stratifies the target population from high to low, and then uses predictive modeling to target high risk patients. (MGSH and MUMH) | TEC-C will leverage this technology as one of many ways frail elders may be identified for enrollment. |
| Renewed focus on the Bridge Clinic (MGSH) | Frail elders referred to the Bridge clinic who are eligible for TEC-C will be considered for enrollment in TEC-C |
| Increase the number of post acute care coordinators that work with patients with high risk conditions, and collaborates with the clinical and case management teams to smoothly transition patients to the next level of care. (MGSH and MUMH) | TEC-C is a care model for frail elders aimed at reducing utilization. Frail elders identified through PACC who are eligible for TEC-C will be considered for enrollment in TEC-C |
| Implement case management in the Emergency Department with the goal of evaluating patients with high needs and ensuring they get access to the resources and programs that they need to transition successfully out of the hospital. (MGSH) | Frail elders eligible for TEC-C who are identified by case management will be considered for enrollment in TEC-C. |
| Increase the number of consultants that work with patients with high risk conditions, and collaborate with the clinical and case management teams to smoothly transition patients to the next level of care. (MUMH) | Frail elders eligible for TEC-C who are identified by consultants will be considered for enrollment in TEC-C. |

# Measurement and Outcome

## 3. A.  Measuring Outcomes:

### Expected Outcomes, Baseline Data and Measures

The expected outcomes, baseline data, and measures for TEC-C are included in Table 7 below.

### Table 7: Core Outcome Measures

| Measure | Definition | Source | Population(s) expected | TEC-C Approach to this measure |
| --- | --- | --- | --- | --- |
| Total hospital cost per capita | Hospital charges per person | HSCRC Casemix Data | All population for covered ZIPs, high utilization set, target population if different, each by race/ethnicity | TEC-C will use the JAGS 2014 data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using HSCRC Casemix data and anticipate a 21% reduction in total hospital costs annually for the population of patients enrolled in TEC-C. |
| Total hospital admits per capita | Admits per thousand | HSCRC Casemix Data | All population for covered ZIPs, high utilization set, target population if different, each by race/ethnicity | TEC-C will use the JAGS 2014 data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using HSCRC Casemix data and anticipate a 10% reduction on this measure. |
| Total health care cost per person | Aggregate payments/person | HSCRC Total Cost Report | All population for covered ZIPs, high utilization set, target population if different, , each by race/ethnicity | TEC-C will use a mixture of the JAGS 2014 data and the IAH Medicare Demonstration data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using Medpar data and anticipate a 13% reduction in total health care cost per patient enrolled in TEC-C. |
| ED visits per capita | Encounters per thousand | HSCRC Casemix Data | All population for covered ZIPs, high utilization set, target population if different, , each by race/ethnicity | TEC-C will use the JAGS 2014 data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using Confidential Case Mix Reports and anticipate a 10% reduction in ED visits for patients enrolled in TEC-C. |
| Readmissions | All Cause 30-day Readmits (see HSCRC specs) | CRISP | High utilization set, target population if different, each by race/ethnicity | TEC-C will use a mixture of the JAGS 2014 data and the IAH Medicare Demonstration data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using PAU reports and anticipate a 20% reduction in 30 day readmissions for patients enrolled in TEC-C. |
| Potentially avoidable utilization | (see HSCRC specifications) | PAU Patient Level Reports | High utilization set, target population if different, each by race/ethnicity | TEC-C will use a mixture of the JAGS 2014 data and the IAH Medicare Demonstration data to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using PAU reports and anticipate a 20% reduction in hospitalizations and ED visits for ambulatory care sensitive conditions for patients enrolled in TEC-C. |
| Patient experience | % rating 9 or 10 | HCAPHS | High utilization set, target population if different, each by race/ethnicity | TEC-C will use a mixture of the JAGS 2014 data and experience with MTEC at MedStar Washington Hospital Center to establish a baseline for all patients enrolled in TEC-C (De Jonge et al., 2014). We will monitor this measure annually using survey tool similar to HCAPHS scores and anticipate an average score at 3 out of 4 or higher for patients enrolled in TEC-C. |

*Note: We will stratify all data in Table 7 by race and ethnicity.

### How the Target Population Positively Impacts Key Outcome Measures

While frail elders are small in number, this subgroup of 5% of beneficiaries represents a significant proportion of national Medicare expenditures (De Jonge et al., 2014).  The MTEC model has demonstrated reductions in hospital admissions, total health care costs, ED visits, readmissions, and potentially avoidable utilization for such patients.  In addition, MTEC has demonstrated enhanced patient experience for this population.  We anticipate similar results through the expansion of MTEC to Maryland.

## 3. B.  Measuring Process:

### Baseline Data, Process, and Programmatic Measures

Baseline data, process, and programmatic measures for TEC-C are included in Tables 8-9 below.

### Table 8: Core Process Measures

| Measure | Definition | Source | Population(s) expected | TEC-C Approach to this measure |
| --- | --- | --- | --- | --- |
| Use of Encounter Notification Alerts | % of inpatient discharges that result in an Encounter Notification System alert going to a physician | CRISP | All population for covered ZIPs, high utilization set, target population if different | TEC-C is a home-based care delivery model. The TEC-C team is fully registered with CRISP and receives 100% of the alerts from CRISP. |
| Completion of health risk assessments | % High utilizers with completed Health Risk Assessments | Hospital, Partnership, Collaboration | High utilization set, target population if different | TEC-C screens for eligibility for the MTEC program using a geriatrics health risk assessment at intake. As all patients are screened, we expect 100% completion. |
| Established longitudinal care plan | % of High Utilizers Patients with completed care | Hospital, Partnership, Collaboration | High utilization set, target population if different | TEC-C care teams currently develop and document care plans, goals of care, and advanced directives within the clinical notes for all patients enrolled in TEC-C. TEC-C will continue this method and expect 100% completion. |
| Shared Care Profile | % of patients with care plans with data shared through HIE in Care Profile | CRISP | High utilization set, target population if different | The TEC-C model does not lend itself to this measure. The MTEC approach is designed so that all providers on the MTEC team are informed and updated from a single EHR. |
| Portion of target pop. with contact from assigned care manager | % of High Utilizers Patients with contact with an assigned care manger | Hospital, Partnership, Collaboration | High utilization set, target population if different | The MTEC approach is designed so that each member of the care team works together serves as a collective group of care manager for each patient enrolled in TEC-C. By definition, this measure will be 100% for all patients at all time points. |

### Table 9: Program Specific Measures

| Measure | Definition | Source | Population(s) expected | TEC-C Approach to this Measure |
| --- | --- | --- | --- | --- |
| F/U visit completed within 2 days of hospital discharge or ED visit | Follow-up visit by care team within 2 days of hospital discharge or ED visit | TEC-C programmatic data | All patients enrolled in TEC-C with a hospital discharge or ED visit | TEC-C will use programmatic data to record and monitor time to follow-up visits. We will monitor this measure annually and anticipate over 50% compliance with this measure. |
| Medication reconciliation completed within 2 days after transition from hospital or ED | Medication reconciliation by care team within 2 days of hospital discharge or ED visit | TEC-C programmatic data | All patients enrolled in TEC-C with a hospital discharge or ED visit | TEC-C will use programmatic data to record and monitor time to medication reconciliation. We will monitor this measure annually and anticipate over 50% compliance with this measure |
| Cause of Program Exit | Death, NH placement, Moved, Discharged from Program, Left Program, Other | TEC-C programmatic data | All patients who exit the TEC-C | TEC-C will use programmatic data to record cause of program exit. We will monitor this measure annually and conduct analyses for patterns and trends. |
| Death Data | Location, Code Status, Hospice Involved | TEC-C programmatic data | All patients who died while enrolled in the TEC-C | TEC-C will use programmatic data to record cause of program exit. We will monitor this measure annually and conduct analyses for patterns and trends. |
| Provider Satisfaction / Retention | Overall job satisfaction; Percent of Professional / Admin Staff who leave each year | TEC-C programmatic data | All providers caring for patients | TEC-C will use programmatic data to record how many professional and administrative staff leaves TEC-C each year. We will monitor this measure annually as a percentage, and conduct analyses for patterns and trends. |

# Return on Investment

The TEC-C care model will help move the state of Maryland towards the overall goals and requirements of the new All-Payer Model by decreasing hospital inpatient and outpatient utilization while improving overall quality and satisfaction of care.  The expected ROI for years  2016, 2017, 2018 and 2019 are included in the table below.

### Table 10: Core Return on Investment Measures

| Hospital/RP Name: | CY16 Target Population | CY17 Target Population | CY18 Target Population | CY19Target Population |
| --- | --- | --- | --- | --- |
| - Number of Patients | ## 120 | ## 323 | ## 528 | ## 528 |
| - Number of Medicare and Dual Eligible | ## 120 | ## 323 | ## 528 | ## 528 |
| - Annual Intervention Cost/Patient | ## $13,176 | ## $5,823 | ## $3,532 | ## $3,532 |
| - Annual Intervention Cost (B x C) | ## $1,581,072 | ## $1,882,870 | ## $1,863,492 | ## $1,863,492 |
| - Annual Charges (Baseline) | ## $3,551,968 | ## $9,570,579 | ## $15,618,791 | ## $15,618,791 |
| - Annual Gross Savings (XX% x E) | ## $745,797 | ## $2,009,507 | ## $3,279,433 | ## $3,279,433 |
| - Variable Savings (F x 50%) | ## $372,898 | ## $1,004,754 | ## $1,639,717 | ## $1,639,717 |
| - Annual Net Savings (G-D) | ## $(1,208,174) | ## $(878,117) | ## $(223,776) | ## $(223,776) |
| Add: Non-Hospital Savings | ## $55,034 | ## $148,285 | ## $230,530 | ## $230,530 |
| Add: Total Savings | ## $(1,153,140) | ## $(729,831) | ## 6,754 | ## 6,754 |

The number of patients reached by the TEC-C Model is based on historic experience of staff recruitment and actual patient enrollment. The TEC-C Model is ready for deployment and if the recruitment of staff and patient enrollment  comes to fruition at a quicker pace in Maryland then the timetable to reach breakeven will be prior to CY18.

Though not directly calculated in the ROI, it is expected that the TEC-C Model will also enhance overall patient-engagement in care, thus improving secondary prevention efforts that could positively impact the ROI assumptions above.

As positive ROI is realized.  Payers will benefit through a lower total cost of care and a lower per capita cost for their patients.

4. A. Alignment with Maryland All-Payer Model Goals and Requirements:

The TEC-C aligns with the Maryland All-Payer Model in several ways:

- The TEC-C’s population focus is on the Medicare Fee for Service >65

- The TEC-C will decrease hospital inpatient utilization by 19% and outpatient utilization by 20%, thus decreasing hospital cost of care

- The TEC-C will decrease total cost of care by also reducing post acute care services specifically, skilled nursing facility costs

- The TEC-C will improve the quality measures by reducing readmissions and improving patient satisfaction

## 4. B. Expected Hospital ROI 2017-2019:

The expected ROI is in Table 10 above. A positive ROI of 6,754 is expected by CY2018 with a total of 528 reached patients.

## 4. C. Utilizing, Apportioning, and Applying the ROI:

## Due to the number of reached Medicare Patients, the direct ROI to the hospitals is not expected to be significant. As such, we will look at actual outcomes related to the enrolled patients to refine the ROI.  The Total Cost of Care ROI will provide overall savings to the Medicare Program and we will continue to refine this based on actual outcomes.

## 4. D. Reduction in Total Cost of Care beyond the Hospital:

Based on historical performance, the TEC-C Model  is expected to reduce total cost of care.  The MTEC program in Washington DC demonstrated and published a total Medicare cost savings of 17% over two years compared to a similar matched cohort.  Additionally, the intervention showed a savings of 21% in Skilled Nursing Facility use, fewer sub-specialist outpatient visits and demonstrated improved patient and caregiver satisfaction and experience. We anticipate similar results in Maryland and therefore built the ROI on our proven experience. As we move forward, we plan to monitor and compare the TEC-C outcomes to a similar group with usual care.

# Scalability and Sustainability

## 5. A. Sustainability of the Intervention:

TEC-C and its MTEC care teams serve frail elders who have high symptom burden and functional impairment, which predict greater mortality and higher medical costs, including a risk of emergency department visits, hospital admission, and use of postacute care services (De Jonge et al., 2014).  Providing a single, comprehensive source of home-based medical and social services for frail elders and their families  and directly addresses the Centers for Medicare and Medicaid Services’ “Three Part Aim,” to 1) enhance patient care, 2) improve health outcomes, and 3) lower total costs.

TEC-C is sustainable without additional rate increases in future years, beyond the ongoing amount associated with this award in the following ways:

- The MTEC program has demonstrated success having reduced per capita Medicare costs by 20 percent as part of IAH, and having received a 60% share a $1.8 million payment from CMS in July, 2015 (MedStar Washington Hospital Center, 2015). MTEC’s successful participation in IAH provides evidence of the clinical and financial efficacy of the model.  We hypothesize that Baltimore City  elders enrolled in MTEC teams will also experience similar significant Medicare savings.

- By operating in the proposed TEC-C, the catchment area of the two lead hospitals becomes central to the identification of frail elders eligible for enrollment. As these hospitals which are operating under the GBR capped revenue model begin to reduce utilization and increase quality, margins have the potential to become larger in the long-term. These dollars could be reinvested back into the program to sustain and further expand this population health model.

## 5. B. Expansion of the Intervention:

The long-term vision of TEC-C is to provide Maryland hospitals with a framework and an evidence base for implementation of the MTEC model in their catchment areas. Partnering with GBMC to jointly cover a larger geography promotes the scalability of a standardized approach to the clinical care of frail elders across care delivery settings, including safe hand-offs between settings.   By tracking common outcome metrics and sharing best practices from our respective clinical services, the MTEC model expands its evidence base, and this home-based care for frail elders becomes scalable and sustainable.

This award will allow TEC-C to build upon the existing evidence base of the MTEC model by providing an evidence base for MTEC implementation in Maryland.  This evidence base will allow us to quantify the return on investment as a result of reductions in utilization and increased quality.  TEC-C and MTEC leadership are willing to consult with and train other Maryland hospitals on how to implement the MTEC model.  While the model will require an initial investment in infrastructure for the care teams, the evidence-based return on investment should promote hospital leadership’s willingness to invest in the MTEC model and ultimately position these hospitals to recognize similar savings due to reductions in utilization and increased quality.

## 5. C. Partner Demonstrated Commitment:

MTEC care teams coordinate of every aspect of a patient’s care by addressing both medical and social needs.  For these reasons, TEC-C brings to bear a strong and diverse set of partners already embedded in the frail elders’ communities, thereby fostering a community-level, collaborative commitment to address the medical and social services of frail elders.

The MTEC model is designed to be a tailored approach to the medical and social needs of frail elders.  The TEC-C partners have committed to participate in and support TEC-C to ensure that we can respond to the care needs as they arise for the frail elders in the community, which may include tapping into the services of one or more partners.  To maintain the tailored nature of the service, and maintain the operational freedom of each partner, TEC-C partners are not obligated to provide services to TEC-C patients nor can TEC-C guarantee that our patients will use the services a partner renders. However, partnering organizations may find that participating in TEC-C may increase use of the organization’s services.  All partners have demonstrated this level of commitment as evidenced in the letters of commitment in Appendix D.  On an ongoing basis, TEC-C will continue to foster the engagement of partners through weekly team meetings to discuss the care of patients, opportunities, challenges, insights, and effective implementation of MTEC.

# Participating Partners and Decision-Making Process

## 6. A. Participating Partners and Shared Decision Making Process

TEC-C is designed to function as a true collaborative for the effective care of frail elders enrolled in MTEC.  Therefore, regular forums involving the mobile care teams, clinical partners, and community partners are essential to foster a shared decision-making process around care plans, challenges, and opportunities.  TEC-C has weekly care team meetings where all teams and partners are invited to attend.

## 6. B. Formalized Governance Structure

The formalized governance structure of TEC-C is included in Appendix C.  In this structure, the patient is at the center of TEC-C.  Given this paradigm, we have “flipped” the traditional top-down nature of our governance chart and include the patient and the services received toward the top and programmatic leadership at the bottom.

The current clinical and administrative leaders for MTEC will function as the clinical and administrative leaders for TEC-C.  These individuals will be responsible for the overall leadership of the collaborative, including the MTEC program.  TEC-C clinical, community, “other” partners will directly interface and collaborate with the mobile care teams in MTEC.  The monitoring and evaluation partners will work with data, information systems, billing, and financial specialist to ensure accurate and timely reporting of key measures.

## 6. C. Roles, Responsibilities, and Funding for each Partner

Section 2 provides detailed descriptions of the roles and responsibilities for each participating.  Table 11 below briefly describes the role of each partner and the proposed funding mechanism for each partner in TEC-C.  Partners indicated as receiving “No direct funds from award” will not receive funds directly from this award, but may realize increased service utilization as TEC-C identifies the need for frail elders enrolled in the program to utilize partner services.  This may result in increased revenue for these partners.  Partners indicated as receiving “Support from hospital rates” may have costs associated with TEC-C services that are included in the budget to be awarded through the lead hospitals’ rates. Each partner has agreed to this model. If the HSCRC adjusts a Hospital’s Revenue for Rate Capacity or other issues, we request that the funding is separate and distinct so not to inadvertently reduce the amount of the Grant.

### Table 11: Partner Roles and Funding

| Partner Name | Role | Funding |
| --- | --- | --- |
| MedStar Good Samaritan Hospital | Lead Hospital | Increased hospital rates |
| MedStar Union Memorial Hospital | Lead Hospital | Increased hospital rates |
| GBMC Support Our Elders | Clinical Partners | No direct funds from award |
| Action in Maturity (AIM) | Community Partner | No direct funds from award |
| Brinton Woods | Community Partner | No direct funds from award |
| Gilchrist Hospice Care | Community Partner | No direct funds from award |
| Keswick Multi-Care Center | Community Partner | No direct funds from award |
| Stadium Place | Community Partner | No direct funds from award |
| MGSH’s Center for Successful Aging | Other Partner | Support from hospital rates |
| MedStar Visiting Nurses Association | Other Partner | Support from hospital rates |
| MedStar Institute for Innovation | Other Partner | Support from hospital rates |
| MedStar Health Research Institute | Monitoring and Evaluation | Support from hospital rates |
| JEN Associates, Inc. | Monitoring and Evaluation | Support from hospital rates |

# Other Proposal Requirements

# Implementation Work Plan

### Please see the separate pdf file as part of this proposal submission.

# Budget and Expenditures

| Hospital/Applicant: | MedStar Good Samaritan Hospital & MedStar Union Memorial Hospital |
| --- | --- |
| Number of Interventions: | One (Total Elder Care-Collaborative) |
| Total Budget Request ($): | $ 1,882,870 (full year) Permanent Funding |

## 8. A. Line Item Budget on Template

| Workforce/Type of Staff | Description | Amount |
| --- | --- | --- |
| Mobile Patient Care Teams Data analytics | Includes physicians, nurse practitioners, social workers, care coordinators, office triage nurse , team manager, and community outreach liaison Additional data analytic support for total cost evaluation, clinical outcomes, patient experience , and HSCRC reporting | $1,938,509 |
| IT/Technologies | Description | Amount |
| Information Technology to support mobile care teams | Includes laptops with broadband air cards, cell phones, IT server configuration & ongoing support to access patient information (includes internal MedStar data & external CRISP alerts) within HIPPA standards, EMR specialization for population health management (i.e. Time tracking for CCM & CPO billing), improved data management systems for synthesis of patient outcomes & costs, “black bag” medical supplies such as pulse oximeter, stethoscope, B/P cuffs, etc. | $101,463 |
| Other implementation Activities | Description | Amount |
| Personnel regulatory compliance Safety support to clinical teams Community outreach Emergency patient care needs Workflow improvements to enhance provider efficiency & flexibility | Federal & state licensing, credentialing, continuing education, & professional liability Includes security escort services, mileage reimbursement to make house calls, roadside assistance for emergencies. Staff time to cultivate strong working relationships with key care partners and establish presence in targeted neighborhoods. Includes funds used to prevent unnecessary utilization not covered by insurance (i.e. respite care for ongoing caregiver support, medications/supplies not approved through formulary) Includes some modest funding to develop improved scheduling platform that readily interfaces with existing systems intended home-based provider visits (i.e. GPS “Uber”-like taxi dispatch tools) | $103,501 |
| Other Indirect costs | Description | Amount |
| Support personnel New leased office space & supplies Health Information Management-records retention | Includes a portion of executive director and other necessary administrative support personnel Includes new leased office space in targeted geography for team gathering, re-provisioning of supplies, and dispatch Includes office supplies, postage, printing,& fax. Includes some HIM support for patient record management and access | $298,178 |
| Total Expenses/investments | Other reimbursement: Not in template, but part of Total Elder Care is the collection of additional revenue from other sources. Includes fee-for service health insurance billing & Independence at Home Medicare Demonstration Shared savings. Total Expenses/Investments | ($558,781) $1,882,870 |

The following table is the breakdown of each budget category by year:

|  | 2016 | 2017 | 2018* |
| --- | --- | --- | --- |
| Workforce/Type of Staff | $ 1,294,577 | $ 1,938,509 | $ 2,605,107 |
| IT/Technologies | $ 82,688 | $ 101,463 | $ 110,160 |
| Other Implementation Activities | $ 57,260 | $ 103,501 | $ 145,948 |
| Other Indirect Costs | $ 305,579 | $ 298,178 | $ 330,865 |
| Other Reimbursement | $ (159,032) | $ (558,781) | $ (1,328,588) |
| Total Expenses/Investments** | $ 1,581,072 | $ 1,882,870 | $ 1,863,492 |

*2019 is estimated to be the same number of patients and expenditures

** Please note:  TEC plans to staff two teams.  The budget reflects the Medicare FFS portion of the population served by the two teams.

# Budget and Expenditures Narrative

## 9. A. MTEC Intervention:

### Workforce/Type of Staff match

TEC-C  builds on a 15 year proven model in Washington DC. Those teams are currently staffed with a multidisciplinary team of approximately 10 FTEs to care for ~300-350 frail elders in a defined catchment. The new teams planned for eight Baltimore zip codes are staffed similarly (See governance chart in Appendix C) and designed to incrementally grow as patient census increases. Workforce recruitment, team training, and retention are keys to TEC-C success and its biggest expense. TEC-C plans a deep orientation and mentorship with existing DC teams. TEC-C  personnel salaries will be established based on fair market compensation and a small premium for the difficult work of making house calls. Three additional FTEs for data analytics, increased outreach, & HSCRC reporting were added to the budget.  We estimate $1,294,577 in year 2016, $1,938,509 in year 2017, and $2,605,107 in year 2018 for this budget category.

### IT/Technologies

Based on experience from DC-based mobile care teams, TEC-C will require additional investment and support for mobile technologies. Most of the current health system technologies available are designed for hospital /ambulatory use and keep patient information siloed. They are not intended to track a distinct cohort of patients in a neighborhood over time and setting. The existing infrastructure (EMR, scheduling, billing systems) has required creative work-a-rounds and manpower to manage. TEC-C ‘s goal is to streamline the number of systems a team member must access in order to communicate and provide care to a patient.

IT/Technologies include expenses for start-up needs, and modest adaptation. These include laptops with mobile data plans; cell phones; server configuration and support to access patient information under HIPPA standards; some EMR specialization for population health management such as time tracking and interface configuration to CRISP alerts; and “black bag” medical supplies such as pulse oximeters, stethoscopes, B/P cuffs, and wound debridement supplies. Budget amount is based on experience and market rates. We estimate $82,688 in year 2016, $101,463 in year 2017, and $110,160 in year 2018 for this budget category.

### Other implementation Activities

Start-up and expansion of two mobile MTEC teams in Baltimore City is an implementation activity targeted at a high cost population. Additional anticipated implementation expenses are based on past years’ real expenditures in Washington DC.  The following activities are key to implementation and require financial support:

- Clinical personnel regulatory requirements such as federal  & state licensing, credentialing, continuing education, and professional liability

- Adequate safety support to mobile clinical teams and their patients. This includes an on-call security escort service, roadside assistance for emergency needs, mileage reimbursement to make house calls, & incident reporting.

- Community partner engagement. TEC-C will work and coordinate with a myriad of partner agencies such as hospitals, home health agencies for skilled nursing and personal care aides, mobile diagnostic services, home-delivery pharmacies, transportation services, hospice agencies, and local community resources for aging. TEC-C plans to dedicate staff time at start-up to building relationships with key partners. As in DC, TEC-C will include those partners in weekly TEC-C team meetings to communicate and resolve any patient care coordination issues on an ongoing basis. Some funding is set aside to support staff time for relationship building activities.

- Emergency patient care needs. From experience, these include nominal funds ($20K per team per year) to prevent unnecessary utilization events not covered by insurance intended for patients with demonstrated need. Examples include short respite care to prevent caregiver burnout or short-term medication not approved through insurance.

- Workflow improvements to enhance provider efficiency & flexibility. As mentioned previously, adaptation of technology infrastructure to better suit the needs of mobile care teams is still in its infancy. Modest funding has been allocated to new Baltimore teams to develop a better scheduling platform designed to accommodate routine and urgent scheduling by patient location and include some GPS “Uber”-like taxi dispatch and safety tracking tools. Substantial barriers exist in this realm around HIPPA and interface to current systems.

We estimate $57,260 in year 2016, $103,501 in year 2017, and $145,948 in year 2018 for this budget category.

### Other Indirect costs

These costs based on experience and market rates. They Include:

- A portion of executive director and other needed support personnel within TEC-C. These staff provider leadership, advocacy, financial management, operational oversight, and strategic planning to the overall mission of TEC-C.

- New leased office space in targeted geography for team gathering, re-provisioning of supplies, and dispatch of care teams. As well as, needed office supplies, postage, printing, and fax machine.

- Health information management (HIM) support for patient record management and access.

We estimate $305,579 in year 2016, $298,178 in year 2017, and $330,865 in year 2018 for this budget category.

### Other Reimbursements

“Other Reimbursements” are not on the HSCRC grant template, but we have included this line item given the important impact on total costs.  TEC-C plans a similar reimbursement model based on DC experience. These reimbursements includes fee-for service health insurance revenues and Independence at Home (IAH) Medicare shared savings to a subset of eligible patients. The IAH Medicare Demo was expanded for 2 additional years into calendar year 2017. Shared savings payments have been 2 ½ years behind, but as methodology refined, expected payment delays should improve. Not included in this HSCRC budget, but planned for in the Baltimore expansion is participation in Medicare Advantage plan to care for a similar subset of frail, high cost patients. Those revenues, personnel and operating expenses were removed from HSCRC budget. We estimate additional reimbursement for the program in the amounts of $159,032 in year 2016, $558,781 in year 2017, and $1,328,588 in year 2018.

9. B. Total Cost of the Intervention:  Based on the above budget categories, Total Expenses/Investments for TEC-C are $1,581,072 in year 2016, $1,882,870 in year 2017, and $1,863,492 in year 2018.

9. C. Percentage Total Investment Covered by Award:  TEC-C plans a similar reimbursement model based on DC experience. These reimbursements includes fee-for service health insurance revenues and Independence at Home (IAH) Medicare shared savings to a subset of eligible patients.  Therefore, the level of investment is smaller than the full costs of the TEC-C Model.  The Award is estimated to be 91% in CY2016, 77% in CY2017, and 58% in CY2018 of the investment.

9. D. Dispersion of Funds to Partner: No direct incentives will be paid to partners to remain compliant with Stark laws. Patients will be offered a choice among Medicare service providers. Partners may see an increase in service utilization as a result of collaboration.

# Summary of Proposal

| Hospital/Applicant: | MedStar Good Samaritan Hospital; MedStar Union Memorial Hospital |
| --- | --- |
| Date of Submission: | December 18, 2015 |
| Health System Affiliation: | MedStar Health, Inc. |
| Number of Interventions: | One |
| Total Budget Request ($): | $1,882,870 Permanent Funding |

Target Patient Population

The Total Elder Care Collaborative (TEC-C) seeks to demonstrate the efficacy and scalability of the shovel-ready MedStar Total Elder Care (MTEC) home-based primary care model for complex older patients in order to: 1) improve clinical outcomes; 2) improve the patient and family experience; and 3) lower the total costs of care. The TEC-C will achieve this vision by delivering home-based primary care to elders in eight ZIP codes in the county of Baltimore City, including the cities of Baltimore, Roland Park, Govans, Idlewylde, Loch Hill, and Northwood. Unlike traditional disease management programs, the MTEC model of home-based primary care focuses on the overall needs of high-risk elders, regardless of specific disease conditions. The major health needs for this population are functional disability, care coordination, social support services, management of multiple severe chronic illnesses, and palliative and end-of-life care. The targeted geographic area in Baltimore City includes a population of elders that have multiple chronic conditions. The major conditions found in this population include dementia, stroke, psychiatric disease, congestive heart failure, chronic obstructive pulmonary disease (COPD)/respiratory failure, severe chronic kidney disease, cancer, diabetes, hypertension, and falls. Typically, several of these conditions are present in one individual. These frail elders have high symptom burden and functional impairment, which predict greater mortality and higher medical costs, including a risk of emergency department visits, hospital admission, and use of postacute care services (De Jonge et al., 2014).

Summary of program or model for each program intervention to be implemented

Frail elders will receive services from MedStar’s shovel-ready, nationally recognized house call model of primary care (De Jonge et al., 2014). This home-based primary care program was previously known as the Medical House Call Program (MHCP) when developed in Washington D.C. and is now known as MedStar Total Elder Care (MTEC). Since 1999, MedStar Health has operated an MTEC-style program through MedStar Washington Hospital that cares for ill elders at home and across all settings. MTEC teams are guided by four principles: 1) a humane approach to care of frail elders; 2) state-of-the-art diagnostic tests, treatment, and technology at home; 3) coordination of all medical and social services across settings, until the end of life; and 4) economic viability for patients, providers, and payers. MTEC consists of modular and geographically-targeted teams who serve the most ill subgroup of elders in a catchment area, usually within a 20-minute driving radius. Each team module consists of 10 staff, including geriatricians, nurse practitioners, care coordinators, triage nurses, and social workers. The core element of success is ability to offer a single, comprehensive source of home-based medical and social services for patients and their families. Core services include home-based primary care, 24/7 on-call medical staff, continuity to the hospital, intensive social services, and coordination of all specialty and ancillary services. As of 2015, MTEC has served over 3,200 elders in Washington D.C. and has an active census of 620 patients. Each team can serve a total of 300-350 frail elders. The goal of the TEC-C is to demonstrate the scalability of this model to Maryland, beginning with eight targeted ZIP codes in the county of Baltimore City.

Measurement and Outcomes Goals

TEC-C will monitor the following core outcome measures in the population of frail elders enrolled in TEC-C: - Total hospital cost per capita; Total hospital admits per capita; Total health care cost per person; ED visits per capital; Readmissions; Potentially avoidable utilization; Patient experience TEC-C will approach the core process measures in the following way: - TEC-C is a home-based care delivery model. The TEC-C team is fully registered with CRISP and receives 100% of the alerts from CRISP. - TEC-C screens for eligibility for the MTEC program using a geriatrics health risk assessment at intake. As all patients are screened, we expect 100% completion. - TEC-C care teams currently develop and document care plans, goals of care, and advanced directives within the clinical notes for all patients enrolled in TEC-C. TEC-C will continue this method and expect 100% completion. - The MTEC approach is designed so that each member of the care team works together serves as a collective group of care manager for each patient enrolled in TEC-C. By definition, this measure will be 100% for all patients at all time points. TEC-C will monitor the following programmatic measures for patients enrolled in TEC-C: - Follow-up visit completed within 2 days of hospital discharge or ED visit; Medication reconciliation completed within 2 days after transition from hospital or ED; Cause of Program Exit; Death Data; Provider Satisfaction / Retention

Return on Investment. Total Cost of Care Savings

The TEC-C care model will help move the state of Maryland towards the overall goals and requirements of the new All-Payer Model by decreasing hospital inpatient utilization by 19% and outpatient utilization by 20%, thus decreasing hospital cost of care. The TEC-C will decrease total cost of care by also reducing post acute care services specifically, skilled nursing facility costs. Finally, TEC-C will improve the quality measures by reducing readmissions and improving patient satisfaction. A positive ROI of 6,754 is expected by CY2018 with a total of 528 reached patients. The number of patients enrolled is based on historic experience of staff recruitment and actual patient enrollment. As positive ROI is realized. Payers will benefit through a lower total cost of care and a lower per capita cost for their patients

Scalability and Sustainability Plan

TEC-C is sustainable without additional rate increases in future years, beyond the ongoing amount associated with this award in the following ways: - The MTEC program has demonstrated success having reduced per capita Medicare costs by 20 percent as part of IAH, and having received a 60% share a $1.8 million payment from CMS in July, 2015 (MedStar Washington Hospital Center, 2015). We hypothesize that Baltimore City elders enrolled in MTEC teams will also experience similar significant Medicare savings. - By operating in the proposed TEC-C, the catchment area of the two lead hospitals becomes central to the identification of frail elders eligible for enrollment. As these hospitals which are operating under the GBR capped revenue model begin to reduce utilization and increase quality, margins have the potential to become larger in the long-term. These dollars could be reinvested back into the program to sustain and further expand this population health model. This award will allow TEC-C to build upon the existing evidence base of the MTEC model by providing an evidence base for MTEC implementation in Maryland. This evidence base will allow us to quantify the return on investment as a result of reductions in utilization and increased quality. While the model will require an initial investment in infrastructure for the care teams, the evidence-based return on investment should promote hospital leadership’s willingness to invest in the MTEC model and ultimately position these hospitals to recognize similar savings due to reductions in utilization and increased quality.

Participating Partners and Decision-making Process.

TEC-C is designed to function as a true collaborative for the effective care of frail elders enrolled in MTEC. Therefore, regular forums involving the mobile care teams, clinical partners, and community partners are essential to foster a shared decision-making process around care plans, challenges, and opportunities. TEC-C has weekly care team meetings where all teams and partners are invited to attend. The formalized governance structure of TEC-C is positions the patient at the center of TEC-C. Given this paradigm, we have “flipped” the traditional top-down nature of our governance chart and include the patient and the services received toward the top and programmatic leadership at the bottom. The current clinical and administrative leaders for MTEC will function as the clinical and administrative leaders for TEC-C. These individuals will be responsible for the overall leadership of the collaborative, including the MTEC program. TEC-C clinical, community, “other” partners will directly interface and collaborate with the mobile care teams in MTEC. The monitoring and evaluation partners will work with data, information systems, billing, and financial specialist to ensure accurate and timely reporting of key measures.

Implementation Plan

Deployment of the first mobile care team will occur in April 2016. Deployment of the second mobile care team will occur in July of 2017, once the first care team reaches the capacity of 300-350 patients. Other activities that facilitate implementation include: establishing the business structure; executive staffing; clinical staffing; community partner engagement; establishing operational guidelines; leasing facilities and purchasing equipment; and EMR transition.

Budget and Expenditures: Include budget for each intervention

Workforce: TEC-C personnel salaries will be established based on fair market compensation and a small premium for the difficult work of making house calls. Three additional FTEs for data analytics, increased outreach, & HSCRC reporting were added to the budget. We estimate $1,294,577 in year 2016, $1,938,509 in year 2017, and $2,605,107 in year 2018 for this budget category. IT/Technologies: IT/Technologies include expenses for start-up needs, and modest adaptation. These include laptops with mobile data plans; cell phones; server configuration and support to access patient information under HIPPA standards; some EMR specialization for population health management such as time tracking and interface configuration to CRISP alerts; and “black bag” medical supplies such as pulse oximeters, stethoscopes, B/P cuffs, and wound debridement supplies. Budget amount is based on experience and market rates. We estimate $82,688 in year 2016, $101,463 in year 2017, and $110,160 in year 2018 for this budget category. ### Other implementation Activities: Other implementation activities include clinical personnel regulatory requirements, adequate safety support to teams and patients, community partners’ engagement, emergency patient care needs, and workflow improvements to enhance provider efficiency and flexibility. We estimate $57,260 in year 2016, $103,501 in year 2017, and $145,948 in year 2018 for this budget category. Other Indirect Costs: We estimate $305,579 in year 2016, $298,178 in year 2017, and $330,865 in year 2018 for this budget category. Based on the above, total expenses/investments for TEC-C are $1,581,072 in year 2016, $1,882,870 in year 2017, and $1,863,492 in year 2018.

# Appendices

## Appendix A: Map of Coverage Areas for TEC-C and GBMC Support Our Elders

## Appendix B.  Chronic Condition Prevalence by County

DHMH and HSCRC, 2015. Tableau dashboards developed by CRISP. (DHMH & HSCRC, 2015)

Data source:  The data source is CMS’s Chronic Condition Data Warehouse (CCW), which contains 100 percent of Medicare claims for beneficiaries who are enrolled in the fee-for-service (FFS) program as well as enrollment and eligibility data. The information in the Dashboard is restricted to Medicare FFS beneficiaries who were continuously enrolled in Medicare FFS, both parts A and B, for 2012. Beneficiaries who were enrolled in a Medicare Advantage (MA) plan at any point during the year were excluded. Beneficiaries who died during the year were included up to their date of death if they met the other inclusion criteria. The study population includes 34,126,305 FFS Medicare beneficiaries.

The Dashboard includes 17 chronic conditions that are consistent with the conditions suggested by the HHS Strategic Framework on Multiple Chronic Conditions (http://www.hhs.gov/ash/initiatives/mcc/) and is the same set of conditions included in the Office of Information Products and Data Analytics (OIPDA) program statistics examining chronic conditions among Medicare beneficiaries (http://www.cms.gov/Research-Statistics-Data-and-Systems/Statistics-Trends-and-Reports/Chronic-Conditions/index.html). Note that for this analysis, CRISP removed one chronic condition (Autism Spectrum Disorder) due to small cell size.

Chronic conditions are identified through Medicare administrative claims. Medicare beneficiaries were considered to have a chronic condition if the CMS administrative data had a claim indicating that they were receiving a service or treatment for the specific condition. Detailed information on the identification of chronic conditions in the CCW is available at http://www.ccwdata.org/chronic-conditions/index.htm.

CMS is obligated by the federal Privacy Act, 5 U.S.C. Section. 552a and the HIPAA Privacy Rule, 45 C.F.R Parts 160 and 164, to protect the privacy of individual beneficiaries and other persons. All direct identifiers have been removed from this data file. In addition, information is suppressed that is based upon fewer than eleven (11) beneficiaries in the population and is indicated by a blank cell.

- Baltimore

- Baltimore City

## Appendix C.  TEC-C Governance Structure

## Appendix D.  Signed Letters of Commitment

# 12. References

Reference List

Assmann, G. & Schulte, H. (1992). Role of triglycerides in coronary artery disease: lessons from the Prospective Cardiovascular Munster Study. Am.J.Cardiol., 70, 10H-13H.

Baltimore City Health Department (2014). Healthy Baltimore 2015. Baltimore City Health Department [On-line]. Available: http://health.baltimorecity.gov/healthy-baltimore-2015

Boling, P. A. & Leff, B. (2014). Comprehensive longitudinal health care in the home for high-cost beneficiaries: a critical strategy for population health management. J.Am.Geriatr.Soc., 62, 1974-1976.

Centers for Disease Control and Prevention (2014). Conditions that Increase Stroke. Centers for Disease Control and Prevention [On-line]. Available: http://www.cdc.gov/stroke/conditions.htm

Centers for Disease Control and Prevention (2015). Deaths: Final data for 2013 [Detailed tables released ahead of full report]. National vital statistics report. Centers for Disease Control and Prevention [On-line]. Available: http://www.cdc.gov/nchs/data/nvsr/nvsr64/nvsr64_02.pdf

Centers for Medicare & Medicaid Services (2015). Independence at Home Demonstration. Centers for Medicare & Medicaid Services . Centers for Medicare & Medicaid Services [On-line]. Available: https://innovation.cms.gov/initiatives/independence-at-home/

Congress of the United States Congressional Budget Office (2005). The Budget and Economic Outlook: Fiscal Years 2006 to 2015. Congress of the United States Congressional Budget Office [On-line]. Available: https://www.cbo.gov/sites/default/files/109th-congress-2005-2006/reports/01-25-budgetoutlook.pdf

De Jonge, K. E., Jamshed, N., Gilden, D., Kubisiak, J., Bruce, S. R., & Taler, G. (2014). Effects of home-based primary care on Medicare costs in high-risk elders. J.Am.Geriatr.Soc., 62, 1825-1831.

Department of Health and Human Services (2010). Healthy people 2020. Department of Health and Human Services [On-line]. Available: http://www.healthypeople.gov/

DHMH & HSCRC (2015). CMS' Medicare Chronic Condition Data - Prevalence in Maryland Counties. DHMH & HSCRC. DHMH & HSCRC [On-line]. Available: http://www.hscrc.maryland.gov/rp-exhibit-1.cfm

Edes, T., Kinosian, B., Vuckovic, N. H., Nichols, L. O., Becker, M. M., & Hossain, M. (2014). Better access, quality, and cost for clinically complex veterans with home-based primary care. J.Am.Geriatr.Soc., 62, 1954-1961.

Fitzpatrick, A. L., Powe, N. R., Cooper, L. S., Ives, D. G., & Robbins, J. A. (2004). Barriers to health care access among the elderly and who perceives them. Am.J.Public.Health, 94, 1788-1794.

Fried, L. P., Ferrucci, L., Darer, J., Williamson, J. D., & Anderson, G. (2004). Untangling the concepts of disability, frailty, and comorbidity: implications for improved targeting and care. J.Gerontol.A Biol.Sci.Med.Sci., 59, 255-263.

Institute for Healthcare Improvement (2015). Institute for Healthcare Improvement: The IHI Triple Aim. Institute for Healthcare Improvement . Institute for Healthcare Improvement [On-line]. Available: http://www.ihi.org/engage/initiatives/tripleaim/Pages/default.aspx

Maryland Department of Health and Mental Hygiene (2013). Maryland state health improvement process. Maryland Department of Health and Mental Hygiene [On-line]. Available: http://www.dhmh.maryland.gov/ship/SitePages/Home.aspx

MedStar Health (2015). Community dashboard. MedStar Health [On-line]. Available: https://medstarhealth.thehcn.net/modules.php?op=modload&name=NS-Indicator&file=index&topic1=County&topic2=Baltimore

MedStar Health (2015). Community Health Needs Assessment. MedStar Health [On-line]. Available: http://ct1.medstarhealth.org/content/uploads/sites/16/2015/06/MedStar_CHNA_2015_FINAL.pdf

MedStar Washington Hospital Center (2015). A Proven Model: National Demonstration Validates Treating Frail Elders in their Home Saves in Medicare Costs. MedStar Washington Hospital Center [On-line]. Available: http://www.medstarwashington.org/2015/06/18/a-proven-model-national-demonstration-validates-treating-frail-elders-in-their-home-saves-in-medicare-costs/#q={}

National Guideline Clearinghouse, N. (2012). Cardiac arrhythmias in coronary heart disease. A national clinical guideline. National Clearinghouse [On-line]. Available: http://www.guideline.gov/content.aspx?id=10586

Robert Wood Johnson Foundation (2015). County Health Rankings. Robert Wood Johnson Foundation [On-line]. Available: http://www.countyhealthrankings.org/